## Slide 1
Partnership Action Plan
Luxembourg-first sequencing: credibility anchors, community reach, and country expansion bridges
How we sequence partnership outreach
1. Launch support first — Luxembourg institutions + France/Switzerland-linked partners for trust, visibility, and warm intros.
2. Customer reach second — use bilateral chambers, communities, and HR/startup channels to access target users in Luxembourg.
3. Expansion bridges last — country associations are activated only when aligned with the product rollout timeline.
Logo power / trust
Credibility first
Luxembourg institutions
Major chambers & hubs
Media and ecosystem anchors
Examples
Chambers, HoE, UEL, LHoFT, ABBL etc.
Audience access
Customer reach
Country communities in LU
Bilateral chambers
HR / startup / expat networks
Examples
FR, CH Chamber, HRCommunity, FEDIL, HoST, ACA, CFA etc.
Country timing
Expansion bridges
Only when corridor is live
Priority countries before backlog
Defer lower-value logos
Examples
PT,ES, UK, IT chambers of commerce
Decision rule: we contact partners in the order that maximizes launch credibility first, customer acquisition second, and corridor expansion only when timed to the roadmap.
RetirAI · Partnership action plan

## Slide 2
Partnership Rollout Timeline
Use the tracker as the working database; this slide shows only the execution sequence
Weeks 1–4
Launch support
LU + FR + CH
Luxembourg institutions
France & Switzerland-linked partners
Goal: trust, visibility, warm intros
Months 11–12
Portugal wave
PT · Y1
Portugal-linked partners
Prepare first external corridor
Goal: PT community activation
Months 19–20
Spain wave
ES · Y1
Spain-linked partners
Prepare next corridor
Goal: ES community activation
Weeks 27–28
UK wave
UK · Y1
British Chamber
Prepare next corridor
Goal: market-entry bridge
Weeks 35–36
Italy wave
IT · Y1
Italy-linked partners
Prepare next corridor
Goal: market-entry bridge
Key sequencing rule
We do not activate all country associations at once. Outreach is aligned to product readiness and the corridor roadmap, so effort stays concentrated and credible.
Deferred / backlog
Lower-priority country associations stay warm in the tracker, but they move only after launch-country and Y1 expansion priorities are covered.
RetirAI · Partnership rollout aligned to launch and expansion timing